## Sheet1
PRIORITY | PROJECTS | TIMING | BUDGET SOURCE | COST EST. | RESP | COMMENTS
1 | Landscape Plan and Phase 1 restoration of fire damage - | FEB | 66070 Insurance, 21405 Facility Impr. | TBD | TBD | Request for bids from 4 companies (see bid instructions)
2 | Tree Trimming -Collecting bids from tree companies to cut damaged trees. | MARCH |  | 6200 | TBD | Arborists looking at our big trees that may need trimming or fortifying
3 | Select and Replace storage shed |  |  |  | TBD
4 | Termite/Dry rot Damage - Replace posts, fascia, and other areas that have old termite damage and dry rot |  |  |  | Harris
5 | Termite Fumigation | After repairs |  | 4200 | Carol Loren | Received 3 bids for fumigation when repairs are completed.
6 | Kitchen and Bathroom flooring and door replacement |  | 21405 | 11684 | TBD | Contract signed with Gold Coast Construction
7 | Replace floor in Agora Room (to match new floor in kitchen) | 2018 or 2019 | 66120 Sp Projects | 8756 | TBD
8 | South side brush clearance - |  |  |  | Harris | Thin brush below buildings with emphasis on reducing fire danger
9 | Install new thermostat-controlled exhaust fans to ventilate kitchen | 2018 or 2019 | 66120 Sp Projects | 1720 | TBD
10 | Update media cabinet in Agora Room | 2018 or 2019 | 66120 Sp Projects | 800 | TBD
11 | Create a scope of work for church property land use plan | 2018 | Unknown | 5000 | TBD
PERIODIC TASKS
PRIORITY | TASKS | TIMING | BUDGET SOURCE | COST EST. | RESP | COMMENTS
| Semi-annually review water, gas, and electric bills | March, Sept | Not Applicable | Not Applicable
| Annually renew property insurance policy with Church Mutual | October | 66070 Insurance | 5012
| Request Endowment Funds from Council, | Sept. |  | None | Chair | Trustees' portion of Endowment Fund is placed in Funded Acct 21405 (Facility Improvements)
| Parking Lot Maintenance | October | 66120 Sp Projects | 1000 | Chair | Submit requisition to move $1,000 from 2018 account 66120 Special Projects to funded account 21410 Parking Lot Maintenance for 2022 slurry seal
| Update Facilities Rental Use process, rates, and form | August | Not Applicable | Not Applicable | TBD
| Slurry seal and re-stripe parking lot (every five years) | 2022 | 21410 Parking Lot Maint | 5000 | TBD
| Obtain City of Ventura rebate (~$3,000) for campus-wide water usage reduction projects throughout the campus | 2018-01-01 | Not applicable | Unknown | TBD